## Report Developer
Original Developer(s): | Vraj Patel, Andy Lee, Elizabeth Szeto |  |  |  | Knowledge Transfer Sign Off / Date: |  |  | Vraj Patel
(Original Development - Manager)
Role: | Junior Data Engineers |  |  |  | Knowledge Transfer Sign Off / Date: |  |  | Joanne Li
(Recipient - Steady-State Object Owner)
Recipient: | Jasmine Kwok, Joanne Li, Ryan Logue, Jay Louissaint |  |  |  | Knowledge Transfer Sign Off / Date: |  |  | Joanne Li
(Recipient Manager)
KT Object / Project: | HHS Hospital COVID Data Pipeline
Link - Tech Spec: | Team Dasher - Technical Specification Doc.docx |  |  |  | Last Update / Changed By: |  |  | 2025-11-24
Knowledge |  | Knowledge Required |  | Knowledge Transfer |  | Priority | Complexity | Prerequisite | Estimated Transfer | Actual Transfer | KT
|  | Yes | No | Complete | In Progress |  |  |  | Time (Minutes) | Time (Minutes) | Date
A. Data & Domain Understanding | [8 empty] | 12 | 13 | 2025-11-19
1. HHS dataset overview |  | Yes |  | Yes |  | High | Moderate | None | 3 | 3 | 2025-11-19
2. CMS dataset overview |  | Yes |  | Yes |  | High | Moderate | None | 2 | 2 | 2025-11-19
a. Column definitions |  | Yes |  | Yes |  | High | Low | A1, A2 | 3 | 3 | 2025-11-19
b. Data format |  | Yes |  | Yes |  | High | Low | A1, A2 | 1 | 2 | 2025-11-19
c. Rules (eg. used <= total beds) |  | Yes |  | Yes |  | High | Low | A1, A2 | 2 | 2 | 2025-11-19
d. Known issues/data quality issues |  | Yes |  | Yes |  | High | Low | A1, A2 | 1 | 1 | 2025-11-19
B. File Loading Process | [8 empty] | 5 | 6 | 2025-11-19
1. File location |  | Yes |  | Yes |  | High | Low | None | 1 | 2 | 2025-11-19
2. Acceptable file format |  | Yes |  | Yes |  | High | Low | None | 1 | 1 | 2025-11-19
3. How the script reads the file |  | Yes |  | Yes |  | High | Low | A | 1 | 1 | 2025-11-19
4. Read errors |  | Yes |  | Yes |  | High | Low | B3 | 1 | 1 | 2025-11-19
5. How errors are displayed |  | Yes |  | Yes |  | Moderate | Low | B4 | 1 | 1 | 2025-11-19
C. Data Cleaning & Validation | [8 empty] | 13 | 16 | 2025-11-24
1. Cleaning |  | Yes |  | Yes |  | High | Moderate | B | 9 | 10 | 2025-11-19
a. Numeric value cleaning |  | Yes |  | Yes |  | High | Moderate | B | 3 | 3 | 2025-11-19
b. Text cleaning |  | Yes |  | Yes |  | High | Moderate | B | 3 | 4 | 2025-11-19
c. Type conversion |  | Yes |  | Yes |  | High | Moderate | B | 3 | 3 | 2025-11-19
2. Validation rules |  | Yes |  | Yes |  | High | Moderate | C1 | 2 | 3 | 2025-11-19
3. What happens when row fails |  | Yes |  | Yes |  | High | Moderate | C2 | 2 | 3 | 2025-11-24
D. Database Loading | [8 empty] | 23 | 26 | 2025-11-24
1. Database connection method |  | Yes |  | Yes |  | High | Moderate | B | 1 | 1 | 2025-11-19
2. Table structures |  | Yes |  | Yes |  | High | Moderate | A | 10 | 12 | 2025-11-19
a. Column names |  | Yes |  | Yes |  | High | Moderate | A | 3 | 5 | 2025-11-19
b. Data types |  | Yes |  | Yes |  | High | Moderate | A | 5 | 5 | 2025-11-19
c. Primary keys |  | Yes |  | Yes |  | High | Moderate | A | 2 | 2 | 2025-11-19
3. Insert logic |  | Yes |  | Yes |  | High | Moderate | C, D1, D2 | 10 | 10 | 2025-11-19
4. Conflict handling |  | Yes |  | Yes |  | High | Moderate | D1, D2, D3 | 2 | 3 | 2025-11-24
E. Error Handling | [8 empty] | 10 | 11 | 2025-11-24
1. Types of errors |  | Yes |  | Yes |  | High | Moderate | B, C, D | 8 | 8 | 2025-11-19
a. File read errors |  | Yes |  | Yes |  | High | Moderate | B | 2 | 2 | 2025-11-19
b. Data validation error |  | Yes |  | Yes |  | High | Moderate | C | 2 | 2 | 2025-11-19
c. Data constraint violations |  | Yes |  | Yes |  | High | Moderate | D | 4 | 4 | 2025-11-19
2. Error reporting |  | Yes |  | Yes |  | High | Moderate | E1 | 2 | 3 | 2025-11-24
F. Running the files | [8 empty] | 2 | 2 | 2025-11-19
1. Running locally via python script |  | Yes |  | Yes |  | High | Low | B, D | 2 | 2 | 2025-11-19
a. Required libraries, versions |  | Yes |  | Yes |  | High | Low | F1 | 1 | 1 | 2025-11-19
b. Database credentials |  | Yes |  | Yes |  | High | Low | F1 | 1 | 1 | 2025-11-19
G. Maintenance | [8 empty] | 3 | 3 | 2025-11-19
1. How to update mappings or table structure with new columns |  | Yes |  | Yes |  | High | Moderate | D | 1 | 1 | 2025-11-19
2. How to adjust validation rules |  | Yes |  | Yes |  | High | Moderate | C | 1 | 1 | 2025-11-19
3. How to add new fields to table |  | Yes |  | Yes |  | High | Moderate | C, D | 1 | 1 | 2025-11-19